## Sheet1
Asset Name / Process | Identified Security Gap | NIST CSF 2.0 Mapping | Likelihood | Impact | Total Risk Score | Risk Categorization | Proposed Remediation
Fulfillment Database | Legacy local server storing PII | ID.AM-01, PR.DS-01 | 3 | 3 | 9 | HIGH | Move to the cloud entirely or have the server more secured and have a proper backup, which is constantly maintained in case of issues.
LogiCloud (Cloud Saas) | Chosen because it is the “cheapest”.Lack of Due Diligence & Third-Party Vendor Risk Management (TPRM) | ID.AM-02 | 2 | 2 | 4 | MED | Have proper research of the best cost-effective solution and use it
Device and Asset Deployment | Direct connection to the office Wi-Fi, employees have full admin rights giving them permission to install anything, which is extremely dangerous if any account is hacked or a phishing attempt is not seen | PR.AA-01, PR.AA-02, PR.AA-06, ID.AM-01 | 3 | 3 | 9 | HIGH | Least privilige. Employees must only have access to the bare minimum so they can properly do their job. New laptops and installations of software must be done by a dedicated SYS admin.
Remote Work and Access | No VPN and multi-factor authentication for remote work | PR.AA-01, PR.AA-02, PR.AA-06 | 2 | 3 | 6 | MED | Configure VPN and firewall. Have multi-factor authentication.
Password and Account Sharing | Single, shared password across all 15 accounts with no regular changes. | PR.AA-05, PR.AA-01, PR.AA-02, PR.AA-06, ID.AM-01 | 3 | 3 | 9 | HIGH | Create a password policy. Each account must have a different password according to the policy and regular changes (once every 2 months). Configure multi-factor authentication and VPN .
Local server logs | Deleted every 30 days, which leads to loss of critical information | ID.AM-01, PR.DS-01, PR.IR-02, PR.IR-03 | 3 | 2 | 6 | MED | Implement a Centralized Log Management (CLM) system or syslog forwarding to an immutable cloud bucket with a 90-day baseline retention policy.
External USB plugged into the server | Easy access to the USB. Furthermore, it can be damaged. | ID.AM-01, PR.DS-01, PR.IR-02, PR.IR-03 | 3 | 2 | 6 | MED | Have a proper server for backups or use a cloud based service with regular updates to the most recent version of the server
Phishing link clicked | No IDS, no phishing policy, no awereness training. | PR.AT-01, DE.CM-03, DE.CM-01 | 2 | 2 | 4 | MED | Have awereness training and a policy on how to spot phishing emails. Set up an IDS to monitor for such threats